## Sheet1
Epic | Feature | User Story | Task | Work Item Type
Phase 1 – Discovery and Feasibility Study | Define AI Project Scope | As a PM, I want to define clear AI objectives so that the team can focus efforts and track KPIs. | Draft objectives and tie them to measurable KPIs. | Epic
Phase 1 – Discovery and Feasibility Study | Define AI Project Scope |  | Estimate project schedule using T-shirt sizing (S/M/L). | Epic
Phase 1 – Discovery and Feasibility Study | AI Market & Feasibility Research | As a strategist, I want to analyze the AI landscape to understand trends and competitive positioning. | Conduct market research and summarize findings. | Feature
Phase 1 – Discovery and Feasibility Study | AI Market & Feasibility Research |  | Complete technical and financial feasibility analysis. | Task
Phase 1 – Discovery and Feasibility Study | Legal & Ethical Analysis | As a compliance officer, I want to ensure the AI project aligns with GDPR and other regulations. | Document legal/ethical risks and plans. | Feature
Phase 1 – Discovery and Feasibility Study | Legal & Ethical Analysis |  | Get stakeholder buy-in and sign-offs. | Task
Phase 1 – Discovery and Feasibility Study | Team Onboarding & Planning | As a PM, I want to onboard the core team so the project has the right people from the start. | Define roles for PM, Data Engineer, AI Scientist, QA, etc. | Feature
Phase 1 – Discovery and Feasibility Study | Team Onboarding & Planning |  | Secure domain expert availability. | Task
Phase 2 – Data Preparation and Model Selection | Dataset Management | As a data engineer, I want clean and normalized data so that models train effectively. | Collect raw datasets. | Feature
Phase 2 – Data Preparation and Model Selection | Dataset Management |  | Clean, transform, and augment the data. | Task
Phase 2 – Data Preparation and Model Selection | Model Evaluation | As an AI scientist, I want to shortlist models to evaluate which one best fits our project needs. | Research candidate models. | Feature
Phase 2 – Data Preparation and Model Selection | Model Evaluation |  | Run initial benchmarks and testing. | Task
Phase 2 – Data Preparation and Model Selection | AI Platform & Resource Setup | As a DevOps engineer, I want to prepare the AI platform so the team can train and test efficiently. | Setup AI development environment (cloud or on-prem). | Feature
Phase 2 – Data Preparation and Model Selection | AI Platform & Resource Setup |  | Validate availability of computational resources. | Task
Phase 2 – Data Preparation and Model Selection | Stakeholder Confirmation | As a PM, I want sign-offs before prototyping begins. | Review benchmark target and data prep outcomes with stakeholders. | Feature
Phase 3 – Prototype and Experimentation | Prototype Development | As an engineer, I want to build an MVP so we can test the integration of the AI model. | Design and build the prototype application. | Feature
Phase 3 – Prototype and Experimentation | Prototype Development |  | Implement model integration. | Task
Phase 3 – Prototype and Experimentation | QA & Risk Management | As a QA lead, I want to test the prototype’s accuracy and identify biases. | Onboard QA team and run QA process. | Feature
Phase 3 – Prototype and Experimentation | QA & Risk Management |  | Conduct risk assessment (bias, performance). | Task
Phase 3 – Prototype and Experimentation | Stakeholder Feedback Loop | As a PM, I want feedback from stakeholders to refine the prototype. | Collect and analyze experiment results. | Feature
Phase 3 – Prototype and Experimentation | Stakeholder Feedback Loop |  | Document feedback and prepare iteration plan. | Task
Phase 4 – Production Deployment and Evolution | Go-Live Planning | As an engineer, I want to deploy the AI solution to production to meet business needs. | Finalize and execute the deployment plan. | Feature
Phase 4 – Production Deployment and Evolution | Go-Live Planning |  | Conduct UAT with QA. | Task
Phase 4 – Production Deployment and Evolution | Performance Monitoring | As an operator, I want to monitor real-time performance and identify issues quickly. | Set up performance dashboards and alerts. | Feature
Phase 4 – Production Deployment and Evolution | Performance Monitoring |  | Implement user feedback mechanisms. | Task
Phase 4 – Production Deployment and Evolution | Support & Evolution | As a support lead, I want a process for issue resolution and updates. | Log support issues and fixes. | Feature
Phase 4 – Production Deployment and Evolution | Support & Evolution |  | Define a regular update cycle based on KPIs and feedback. | Task